## Sheet1
Requirement | Requirement Type | Parent | Sprint/Release | Epic | Releases | Sprints | Dates
Landing Page | Epic | NA | Release 1 | Landing Page | Release 1 | Sprint 1 | Apr 4 - Apr 15 2022
Flight Management | Feature | Landing Page | Sprint 1 & 2 |  |  | Sprint 2 | Apr 18 - Apr 29 2022
Hotel Management | Feature | Landing Page | Sprint 3 & 4 |  |  | Sprint 3 | May 2 - May 13 2022
Cab Management | Feature | Landing Page | Sprint 5 & 6 |  |  | Sprint 4 | May 16 - May 27 2022
[6 empty] | Sprint 5 | May 30 - Jun 10 2022
Search for Flights | Product Backlog | Flight Management | Sprint 1 |  |  | Sprint 6 | Jun 13 - Jun 24 2022
Book Flight | Product Backlog | Flight Management | Sprint 2 |  | Jun 27 2022
Search for Hotels | Product Backlog | Hotel Management | Sprint 3
Book Hotel | Product Backlog | Hotel Management | Sprint 4
Search for Cabs | Product Backlog | Cab Management | Sprint 5
Book Cab | Product Backlog | Cab Management | Sprint 6
UI for Search for Flights | Task | Search for Flights
DB for Search for Flights | Task | Search for Flights
API for Search for Flights | Task | Search for Flights
UI for Book Flight | Task | Book Flight
DB for Book Flight | Task | Book Flight
API for Book Flight | Task | Book Flight
UI for Search for Hotels | Task | Search for Hotels
DB for Search for Hotels | Task | Search for Hotels
API for Search for Hotels | Task | Search for Hotels
UI for Book Hotel | Task | Book Hotel
DB for Book Hotel | Task | Book Hotel
API for Book Hotel | Task | Book Hotel
UI for Search for Cabs | Task | Search for Cabs
DB for Search for Cabs | Task | Search for Cabs
API for Search for Cabs | Task | Search for Cabs
UI for Book Cab | Task | Book Cab
DB for Book Cab | Task | Book Cab
API for Book Cab | Task | Book Cab
User Profile | Feature | Landing Page
Login Page | Feature | Landing Page
Home Page | Epic | NA